## Product Backlog
Project Name | PUF Information System | PRODUCT BACKLOG
Project ID | MINF16SOFT
Epic ID | Epic Description | User Story ID | User Story Description | Type | Assignee(s) | Status | Estimated Efforts | Consumed Efforts | ETC | Priority | Planned in Sprint #
INCP | Inception phase | INCP-01 | Discussing with client to understand the overall of expected system. | General | All members | Done | 2 | 2 | 0 | 1 | Inception
|  | INCP-02 | Etablishing team and discussing on client requirement to get the same understanding of expected system. | General | All members | Done | 2 | 2 | 0 | 1 | Inception
|  | INCP-03 | Discussing to find solution and project approach. | General | All members | Done | 4 | 4 | 0 | 1 | Inception
|  | INCP-04 | Installing OpenEduCat and producing the installation guide for all team members. | General | Dat | Done | 1 | 1 | 0 | 1 | Inception
|  | INCP-05 | Installing OpenEduCat for solution review. | General | Huy, Quoc, Trang | Done | 1.5 | 1.5 | 0 | 1 | Inception
|  | INCP-06 | Reviewing OpenEduCat solution and documents to dsfhave overall understanding of supported functional and technical. | General | All members | Done | 4 | 4 | 0 | 1 | Inception
|  | INCP-07 | Defining project methodology, processes, reports, etc. | General | All members | Done | 4 | 4 | 0 | 1 | Inception
|  | INCP-08 | Practicing on OpenEduCat to understand how to customize system in both functional and technical. | General | Huy, Dat | Done | 4 | 4 | 0 | 1 | Inception
|  | INCP-09 | Running demo of standard OpenEduCat system to define the product backlog and prioritties. | General | All members | Done | 8 | 8 | 0 | 1 | Inception
|  | INCP-10 | Defining project roadmap based on defined product backlog. | General | All members | Done | 2 | 2 | 0 | 1 | Inception
|  | INCP-11 | Producing Use Case Model to prepare User Role Menu. | General | All members | Done | 4 | 4 | 0 | 1 | Inception
|  | INCP-12 | Setting up technical environments to prepare for the first Sprint. | General | All members | Done | 2 | 2 | 0 | 1 | Inception
|  | INCP-13 | Reviewing technical environments to prepare for Sprint 1. | General | Dat | Done | 1 | 1 | 0 | 1 | Inception
|  | INCP-14 | Updating project final report. | General | Huy | Done | 0.5 | 0.5 | 0 | 1 | Inception
CONF | Configuration | CONF-01 | Setup UAT server for demo and testing | General |  | Done | 8 | 8 | 0 | 3 | 1
|  | CONF-02 | Standard menu for all users | General |  | Done | 4 | 8 | 0 | 1 | 1
|  | CONF-03 | Menu for student | General |  | Done | 4 | 8 | 0 | 1 | 1
|  | CONF-04 | Menu for faculty | General |  | Done | 4 | 8 | 0 | 1 | 1
|  | CONF-05 | Menu for back office | General |  | Pending |  |  |  | 1
|  | CONF-06 | Updating logo for PUF | General |  | Pending |  |  |  | 3
ENRO | Enrollment / Admission | [8 empty] | 2
STUD | Student | STUD-01 | Modifying student fields | Requirements |  | Done | 6 | 12 | 0 | 1 | 1
FACU | Faculty | FACU-01 | Modifying faculty fields | Requirements |  | Done | 6 | 12 | 0 | 1 | 1
COBA | Course / Batch | [8 empty] | 1
ASGN | Assignment | [8 empty] | 2
CLSR | Classroom | [8 empty] | 1
FINA | Financial / Fees | [8 empty] | 3
TMTB | Time Table | [8 empty] | 1
ATED | Attendances | [8 empty] | 1
EXAM | Exam and Results | [8 empty] | 1
EVEN | Events | [8 empty] | 3
NEWS | News | [8 empty] | 3
DHIS | Data history/revision | DHIS-01 | Managing all updates on record | Requirements |  | Done | 8 | 12 | 0 | 1 | 1
WEBD | Web Design | [8 empty] | 2
TOTALS | [6 empty] | 80 | 108 | 0
*** Please note that Priority 1 is higher than Priority 2 and so on.
*** Please note that effort is in hours
Note on G3: Rohit Garg: User Story / User Scenarios having Status as "Ongoing" or "Complete" will cease to have an impact on the calculation of Priority.
Note on H3: Rohit Garg: Initial Estimate based on Estimated Size
Note on L3: Rohit Garg: Please enter the Sprint Number, in which the User Story is planned.

## Sprints Release Plan
Project Name | PUF Information System | SPRINTS PLAN
Project ID | MINF16SOFT
Total Number of Sprints Planned |  |  | 5
Sprint Duration (in Working Days) |  |  | 15
Sprint # | Sprint Start Date | Days | Sprint End Date | Estimated Efforts | Consumed Efforts | ETC | Status | Release # | Release Date
Inception | 2018-03-09 | 5 | 2018-03-16 | 40 | 40 | 0 | Completed
1 | 2018-03-19 | 15 | 2018-04-20 | 40 | 68 | 0 | Planned
2 | 2018-04-23 | 14 | 2018-05-11 | 0 | 0 | 0 | Planned
3 | 2018-05-14 | 13 | 2018-06-01 | 0 | 0 | 0 | Planned
4 | 2018-06-04 | 15 | 2018-06-29 | 0 | 0 | 0 | Planned
Please fill the data only in the White Cells, Coloured Cells are AUTO Populated based on the Data filled in the White Cells.
Formulas:
Sprint Start Date = IF(WEEKDAY([Sprint End Date, row above])=6,[Sprint End Date, row above]+3, [Sprint End Date, row above]+1)
Note on A5: Rohit Garg: Please enter the duration in number of working days.
Note on I7: Rohit Garg: Release Number, in which the corresponding Sprint is planned to be released.

## Holidays
Vietnam Public Holidays | Date
King Hung | 2018-04-25
Reunion Day | 2018-04-30
Labor Day | 2018-05-01